## Sheet1
SPL - LAB1
TEAM : 12 | Supervisor : Ridwan Kabir (MRK)
1. Tasfia Barshat ->190042126
2. Talimul Bari Shreshtho -> 190042128
3. Mumtahina Rahman -> 190042129
| Project Start: | 2021-04-01
| WEEK: | 1 |  | 2021-04-01 | [6 empty] | 2021-04-08 | [6 empty] | 2021-04-15 | [6 empty] | 2021-04-22 | [6 empty] | 2021-04-29 | [6 empty] | 2021-05-06 | [6 empty] | 2021-05-13 | [6 empty] | 2021-05-20 | [6 empty] | 2021-05-27 | [6 empty] | 2021-06-03 | [6 empty] | 2021-06-10 | [6 empty] | 2021-06-17 | [6 empty] | 2021-06-24
 | time axis 2021-04-01 to 2021-06-30
TASK | PROGRESS | START | END | time axis 2021-04-01 to 2021-06-30
Phase 1 : Determinig necessary skills and develping |  |  |  | 2021-06-03: MID
1.1 Understanding git | 70% | 2021-04-01 | 2021-04-02
1.2 Basics of javascript javascript dom | 80% | 2021-04-02 | 2021-04-04
1.3 Geting familiar with css and html | 100% | 2021-04-04 | 2021-04-09
1.4 Databse basics | 0% | 2021-04-05 | 2021-04-10
1.5 Simple web game development | 0% | 2021-04-10 | 2021-04-20
Phase 2: Reviewing all features of the site
2.1 Implementing new concepts in small scale | 0% | 2021-04-12 | 2021-04-15
2.2 Researching on differnet teaching methods for children | 0% | 2021-04-12 | 2021-04-17
2.3 Reviewing all skills and concepts | 0% | 2021-04-14 | 2021-04-20
2.4 Reviewing all features and finalising | 0% | 2021-04-18 | 2021-04-20
Phase 3: Proposal and Homepage
3.1 Desging the homepage | 30% | 2021-04-20 | 2021-04-24
3.2 Homepage animations | 0% | 2021-04-22 | 2021-04-25
3.3 Homepage build | 0% | 2021-04-23 | 2021-04-26
3.4 Proposal presentation preparation | 0% | 2021-04-26 | 2021-04-30
Phase 4: User system and resource gathering
4.1 Developing a user system | 0% | 2021-05-01 | 2021-05-05
4.2 Gathering necessaary videos , Resources | 0% | 2021-05-02 | 2021-05-04
4.3 Adding resources to the home page | 0% | 2021-05-04 | 2021-05-06
Phase 5: Review and small game development
5.1 Review all the works have been done till now and change if necessary | 0% | 2021-05-04 | 2021-05-10
5.2 Develop a math related simple game | 0% | 2021-05-08 | 2021-05-18
5.3 Develop a number learning game | 0% | 2021-05-08 | 2021-05-18
5.4 develop a game for alphabet learning | 0% | 2021-05-08 | 2021-05-18
Phase 6: Final proposal and learning pages
6.1 Preparing the final proposal and reviewing all progress | 0% | 2021-05-09 | 2021-05-14
6.2 Making necessary changes in plan | 0% | 2021-05-09 | 2021-05-15
6.3 Math learning page | 0% | 2021-05-18 | 2021-05-22
6.4 Memorizing practice page | 0% | 2021-05-18 | 2021-05-24
6.5 Color recognizing , animal recognizing page | 0% | 2021-05-18 | 2021-05-26
6.6 Testing all pages | 0% | 2021-05-26 | 2021-05-28
Phase 7: Test syatem and rewads
7.1 Quizz for math learning page | 0% | 2021-05-27 | 2021-05-30
7.2 Quizz for memorizing | 0% | 2021-05-27 | 2021-05-30
7.3 Quizz for alphabets , animals etc | 0% | 2021-05-27 | 2021-05-30
7.4 Testing the quizz/test system | 0% | 2021-05-31 | 2021-06-03
7.5 Make necessary changes if necessary | 0% | 2021-06-01 | 2021-06-03
7.6 Make an reward system for correct answer / full sessions | 0% | 2021-06-01 | 2021-06-03
Mid term Exam Break
Phase 8: Databse , Data collecting , Producing feedback | 0%
8.1 Develop a database for the site | 0% | 2021-06-25 | 2021-06-28
8.2 Arrangement system for all the data collected from the user | 0% | 2021-06-27 | 2021-06-28
8.3 Feedback system development | 0% | 2021-06-26 | 2021-07-02
8.4 Live chart system for showcasing succes of any method | 0% | 2021-06-28 | 2021-07-03
Phase 9: Review,Bug fixing,Final presentation,Github readme
9.1 Review all code | 0% | 2021-07-03 | 2021-07-08
9.2 Bug fix | 0% | 2021-07-01 | 2021-06-10
9.3 Make necessary changes | 0% | 2021-07-05 | 2021-06-12
9.4 Test the site | 0% | 2021-07-10 | 2021-06-15
9.5 Prepare git readme file | 0% | 2021-07-10 | 2021-07-19